## README & Disclosure
MAL-FRT-001 — GRC Findings & Remediation Tracker
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
MindfulAI Labs · Simulated GRC Practice Environment · AI GRC & Control Assurance Portfolio
Document Control
Document ID | MAL-FRT-001
Document Title | GRC Findings & Remediation Tracker
Version | 1.0
Prepared By | Maxine Jones, GRC Analyst
Prepared Date | October 21, 2026
Classification | Confidential — Internal Use Only
Status | Final — Portfolio Simulation
Purpose and Basis
Purpose | Consolidates the documented findings, process-improvement observations, planning gaps, remediation actions and evidence requirements from ten MindfulAI Labs control artifacts (MAL-CHK-001 through MAL-VRA-010) into one filterable tracker.
Basis | Built exclusively from the ten MAL-xxx source documents and the six JSON exports (Asset Register, Risk Register, Control Register, Policies, Risk Appetite Statements, KRIs). Nothing here was drawn from outside those sources.
Simulation disclosure | SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
What this tracker does NOT contain | No invented findings, remediation actions, completion dates, management approvals, evidence, closure results, residual risk scores or risk-tolerance conclusions. No suggested closure criteria. Every sign-off table in the source documents is blank; no approvals are represented here.
Record Classifications (Findings tab)
Confirmed Finding (Simulated) | A control deficiency or exception that the source document explicitly records as a finding or exception within the simulated scenario (ACR-xx, VUL-01/02, PRV-01/02, LOG-01/02, VRA-01/02/03).
Observation | A source-labelled observation: process-improvement observations (OBS-01, VUL-03, PRV-03, LOG-03, VRA-04), risk-register coverage gaps, and one asset-register observation. The source states these are not control exceptions.
Planning Gap | A pre-assessment planning observation (APO-01 to APO-04) in MAL-CAP-009. The source states these are not findings and not control deficiencies; no testing was performed.
Evidence Requirement | An item marked “Evidence Required — Not Provided (Simulated Requirement)”. Kept on its own tab. A missing-evidence item is NOT a control deficiency and is never counted as one.
Reported Status vs. Validated Closure
Rule | “Status (As Documented)” is the status stated in the source document. “Independent Closure Validation” is a separate field. No remediation status in this tracker has been independently validated: every record reads “Not performed — evidence not provided”. The one reported remediation (ACR-03, “Remediated (Simulated) — account disabled; underlying process fix Open”) is preserved as written and is NOT counted as closed.
Analyst-derived fields | Columns whose header ends “(Analyst-Derived)” — Severity Group, Primary Owner Team, Reported Status Group — are reporting classifications added for filtering and dashboard counts only. The original wording is always kept in the adjacent “(As Documented)” column.
Target dates | Exact dates are stored as dates. Quarterly targets (e.g., Q4 2026, Q1 2027) are kept as text; no calendar deadline has been assigned to them. “Not stated in source” means the source gives no date.
Closure criteria | Taken verbatim from the source “Validation” statement where one exists. Otherwise “Not Defined in Source”.
Tabs
Summary Dashboard | Formula-driven counts by classification, severity group, status, source document, owner and target timeline; reported vs. validated closure; contextual KRI / risk-appetite / policy references.
Findings | 29 trackable records with source traceability (document, section, original ID).
Remediation Actions | 30 actions, one per source recommendation (ACR-03 is split in two because the source reports two different statuses).
Evidence Requests | 83 evidence requirements, separate from findings.
Source Index | The ten source documents, with documented counts reconciled to extracted counts.
ID Crosswalk | Source IDs ↔ normalized IDs for assets, risks and controls; policy references. Normalized IDs are shown only where a source document states them.
Data Dictionary | Every column, its allowed values and where its content comes from.
Scope Notes
Excluded: MAL-IPR-011 | The assessment document for control A.5.35 (independent peer review; Not Tested in the Control Register) was not provided, so it contributes no findings, actions or evidence. The control appears in the ID Crosswalk only.
Not logged as findings | Items the sources mark as Met / Passed; blank sign-off tables; scope notes (e.g., assets excluded or deferred to program level in MAL-VMA-005, MAL-BRT-007, MAL-LMA-008); the assessor-independence consideration in MAL-CAP-009; and risk-appetite / KRI context.
Risk appetite and KRIs | Used as context only where a source document cites them. No residual risk scores are stated or computed, and no comparison to risk tolerance is made.
Reconciliation (live formulas)
Trackable records (Findings tab) | 29 | Expected 29
Confirmed Findings (Simulated) | 12 | Expected 12
Observations | 13 | Expected 13
Planning Gaps | 4 | Expected 4
Remediation actions | 30 | Expected 30
Evidence requirements | 83 | Expected 83
Source documents reconciled (Match) | 10 | Expected 10 of 10

## Summary Dashboard
Summary Dashboard
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
All figures are live formulas over the Findings, Remediation Actions, Evidence Requests and Source Index tabs.
As-of date (editable input) | 2026-10-21 | Assumption: set to the preparation date (2026-10-21). Change it to re-run the target-date counts in section 6.
1. Record counts
Measure | Count
Confirmed Findings (Simulated) | 12
Observations | 13
Planning Gaps | 4
Total trackable records (Findings tab) | 29
Remediation actions (Remediation Actions tab) | 30
Evidence requirements (separate from findings) | 83
Evidence requirements treated as control deficiencies | 0
2. Reported simulated status vs. independently validated closure
Measure | Records | Remediation Actions
Reported: In Progress (Simulated) | 8 | 8
Reported: Open (Simulated) | 10 | 11
Reported: Reported Remediated (Sim.) — Process Fix Open | 1 | 0
Reported: Accepted by Owner (per source) | 1 | 1
Reported: No Status in Source | 9 | 9
Reported: Remediated (Simulated) — account disabled (ACR-03 action split) | n/a | 1
Total (reconciles to section 1) | 29 | 30
Independently validated closures | 0 | 0 | Zero: no closure evidence exists in the simulated scenario
Independent closure validation NOT performed | 29 | 30
3. Severity group (analyst-derived) by classification — original severity wording is on the Findings tab
Severity Group (Analyst-Derived) | Confirmed Findings | Observations | Planning Gaps | Total
High | 2 | 0 | 0 | 2
Medium-High | 1 | 0 | 0 | 1
Medium | 9 | 0 | 0 | 9
Low | 0 | 8 | 0 | 8
Not Rated | 0 | 5 | 4 | 9
Total | 12 | 13 | 4 | 29
4. By source document and control rating
Source Document | Control Rating (Source) | Findings | Observations | Planning Gaps | Evidence Requirements | Reconciliation
MAL-CHK-001 — AI Training Data Validation Checklist | Effective | 0 | 1 | 0 | 5 | Match
MAL-ACR-002 — User Access Review Worksheet | Partially Effective | 3 | 0 | 0 | 6 | Match
MAL-CTW-003 — Change Management Control Test Worksheet | Effective | 0 | 1 | 0 | 7 | Match
MAL-STD-004 — Privileged Access & Multi-Factor Authentication Security Standard | Effective | 0 | 1 | 0 | 9 | Match
MAL-VMA-005 — Vulnerability Management Control Assessment / Test Report | Partially Effective | 2 | 2 | 0 | 7 | Match
MAL-PIA-006 — AI Privacy Impact Assessment (DPIA-Aligned) | Partially Effective | 2 | 2 | 0 | 7 | Match
MAL-BRT-007 — Backup & Recovery Test Record | Effective | 0 | 1 | 0 | 8 | Match
MAL-LMA-008 — Security Logging & Monitoring Control Assessment | Partially Effective | 2 | 3 | 0 | 8 | Match
MAL-CAP-009 — Compliance Assessment Plan & Evidence Request | Not Tested (Effectiveness Not Concluded) | 0 | 0 | 4 | 12 | Match
MAL-VRA-010 — Third-Party AI Vendor Risk Assessment | Ineffective | 3 | 2 | 0 | 14 | Match
Total |  | 12 | 13 | 4 | 83 | All Match
5. Records by primary owner team (analyst-derived from the documented owner)
Primary Owner Team | Confirmed Findings | Observations | Planning Gaps | Total
IAM Team | 3 | 1 | 0 | 4
Data Science Team | 0 | 1 | 0 | 1
AI Engineering Team | 0 | 1 | 0 | 1
Application Security Team | 2 | 2 | 0 | 4
Privacy and Compliance Team | 2 | 2 | 0 | 4
Infrastructure Operations Team | 0 | 1 | 0 | 1
Security Operations Team | 2 | 2 | 0 | 4
Third-Party Risk Management Team | 3 | 2 | 0 | 5
GRC Team | 0 | 0 | 1 | 1
Not specified in source | 0 | 1 | 3 | 4
Total | 12 | 13 | 4 | 29
6. Target timeline (quarter targets stay as text; no calendar date is assigned to them)
Target | Records
Exact date in October 2026 | 3
Exact date in November 2026 | 4
Exact date in December 2026 | 6
Quarter target: Q4 2026 (text) | 2
Quarter target: Q1 2027 (text) | 4
Target not stated in source | 10
Total (reconciles to section 1) | 29
Exact target dates within 30 days of the as-of date | 4 | Counts exact dates only; reported status is unchanged by this view
Exact target dates earlier than the as-of date | 0
7. Context only — cited by the source documents (not used to rate, score or conclude)
Item | Current / Level | Thresholds / Tolerance | Trend | Owner | Cited In |  | Limitation stated by the source
KRI-001 Critical AI Validation Exceptions | 1 (count) | Amber 2 / Red 4 | Stable | Clinical AI & ML Team | MAL-CAP-009 §6.4 |  | Does not measure CTL-009 and is not evidence that annual compliance assessments occur.
KRI-006 Critical Vendors with Overdue Risk Assessments | 3 (count) | Amber 4 / Red 6 | Decreasing | Third-Party Risk Management Team | MAL-VRA-010 §6.2 |  | Counts overdue reassessments of vendors on record; does not evidence pre-approval assessment and does not override the control assessment.
RAS-001 AI Governance (Cautious) | Tolerance max 8 of 25 | Board approved | n/a | n/a | MAL-CAP-009 §6.3 |  | Contextual only; not a Compliance appetite statement. No residual score exists for a compliance risk, so no comparison is made (APO-04).
RAS-006 Third-Party (Moderate) | Tolerance max 10 of 25 | Board approved | n/a | n/a | MAL-VRA-010 §6.1 |  | No third-party risk exists in the register, so no residual score exists and no inside/outside-tolerance statement is made.
The other KRIs (KRI-002 to KRI-005) and appetite statements (RAS-002 to RAS-005) in the JSON exports are not cited by any source document in scope and are not used. Policies cited by CAP-009 are listed on the ID Crosswalk tab.

## Findings
Findings, Observations & Planning Gaps
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
One row per trackable record. Original wording is preserved in “(As Documented)” columns; “(Analyst-Derived)” columns are reporting classifications only.
Tracker ID | Original Source ID | Source Document ID | Source Document Title | Source Section | Related Control | Control Rating (Source Register) | Related Asset | Related Risk | Title (As Documented) | Description (As Documented) | Classification | Subtype | Severity (As Documented) | Severity Group (Analyst-Derived) | Owner (As Documented) | Primary Owner Team (Analyst-Derived) | Recommended Action (As Documented) | Status (As Documented) | Reported Status Group (Analyst-Derived) | Independent Closure Validation | Target Date (As Documented) | Target Date (Exact) | Target Date Type | Evidence Required (Cross-Reference) | Closure Criteria | Rating Impact (As Documented) | Simulation Flag
FRT-001 | OBS-01 | MAL-CHK-001 | AI Training Data Validation Checklist | §6 | CTL-mu0tgvxq — Perform documented bias and data quality validation before AI model approval (ISO 27001 A.5.12) | Effective | AST-002 (source ID AST-mu0set5n) — Financial Risk Training Data Repository | RSK-mu0sxjrj (RSK-001) — Training data bias causes inaccurate clinical AI recommendations (source: this checklist supports data-level bias validation and does not, on its own, close that risk) | OBS-01 — Field Completeness (Minor) | Approximately 0.4% of records contained a missing value in a non-critical, optional field. (Simulated sample figure.) | Observation | Minor Observation (source label) | Not separately rated; Risk / Impact: Low | Low | Data Science Team | Data Science Team | Continue monitoring field completeness in future quarterly validations and confirm the field remains excluded from model input. | Records retained; reviewed and accepted by the Data Science Team | Accepted by Owner (per source) | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Control-level evidence list EVD-001 to EVD-005 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | This observation is minor and does not change the Effective conclusion for the control. | Simulated portfolio scenario
FRT-002 | ACR-01 | MAL-ACR-002 | User Access Review Worksheet | §8–9 | CTL-mu1nugzu — Restrict AI training data repositories to authorized personnel using role-based access (NIST CSF PR.AA-05) | Partially Effective | AST-002 (source ID AST-mu0set5n) — Financial Risk Training Data Repository | RSK-mu0t1uva (RSK-002) — Unauthorized user exploits inadequate data access restrictions causing sensitive data exposure to Financial Risk Training Data Repository | ACR-01 — Outdated Access Following a Role Change (Mover) | Generic test identity U-1043 transferred out of the Analytics function but retained read/write (FRTDR-DataEngineer) access to the repository beyond the effective date of the role change. (Simulated.) | Confirmed Finding (Simulated) | Control Deficiency (Exception) | Medium | Medium | IAM Team (execution), with Data Science Team (resource-owner approval) | IAM Team | Revoke the retained entitlements and incorporate mover events into the joiner/mover/leaver (JML) process, with HR-triggered, automated recalculation of access on role change. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | October 31, 2026 (Simulated) | 2026-10-31 | Exact date | Control-level evidence list EVD-006 to EVD-011 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Cited among the operating exceptions supporting the Partially Effective conclusion (§10) | Simulated portfolio scenario
FRT-003 | ACR-02 | MAL-ACR-002 | User Access Review Worksheet | §8–9 | CTL-mu1nugzu — Restrict AI training data repositories to authorized personnel using role-based access (NIST CSF PR.AA-05) | Partially Effective | AST-002 (source ID AST-mu0set5n) — Financial Risk Training Data Repository | RSK-mu0t1uva (RSK-002) — Unauthorized user exploits inadequate data access restrictions causing sensitive data exposure to Financial Risk Training Data Repository | ACR-02 — Excessive Write Privileges (Least Privilege) | Generic test identities U-1101 and U-1102 were assigned a write/modify role (FRTDR-DataEngineer) although their job function requires read-only (FRTDR-DataScientist) access. (Simulated.) | Confirmed Finding (Simulated) | Control Deficiency (Exception) | Medium-High | Medium-High | IAM Team (execution), with Data Science Team (resource-owner approval) | IAM Team | Downgrade both accounts to read-only; enforce the authoritative role-to-entitlement mapping; require documented business justification and periodic recertification for any write-level access. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | October 31, 2026 (Simulated) | 2026-10-31 | Exact date | Control-level evidence list EVD-006 to EVD-011 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Cited among the operating exceptions supporting the Partially Effective conclusion (§10) | Simulated portfolio scenario
FRT-004 | ACR-03 | MAL-ACR-002 | User Access Review Worksheet | §8–9 | CTL-mu1nugzu — Restrict AI training data repositories to authorized personnel using role-based access (NIST CSF PR.AA-05) | Partially Effective | AST-002 (source ID AST-mu0set5n) — Financial Risk Training Data Repository | RSK-mu0t1uva (RSK-002) — Unauthorized user exploits inadequate data access restrictions causing sensitive data exposure to Financial Risk Training Data Repository | ACR-03 — Delayed Contractor Deprovisioning (Leaver) | Contractor test identity C-207 remained active for approximately 12 days after the contract end date, exceeding the same-business-day deprovisioning expectation for departed personnel. (Simulated.) | Confirmed Finding (Simulated) | Control Deficiency (Exception) | High (window) | High | IAM Team (execution), with HR / Vendor Management (notification of end dates) | IAM Team | Implement event-driven deprovisioning tied to contract end dates; perform leaver reconciliation each quarter; generate alerts for any account active past its associated end date. | Remediated (Simulated) — account disabled; underlying process fix Open | Reported Remediated (Sim.) — Process Fix Open | Not performed — evidence not provided | November 15, 2026 (Simulated) for the process fix | 2026-11-15 | Exact date | Control-level evidence list EVD-006 to EVD-011 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Cited among the operating exceptions supporting the Partially Effective conclusion (§10) | Simulated portfolio scenario
FRT-005 | OBS-01 | MAL-CTW-003 | Change Management Control Test Worksheet | §9 | CTL-mu1nvfmw — Require documented review and approval before production AI model changes are deployed (SOC 2 CC8.1) | Effective | AST-001 — Clinical Diagnostic AI Model (change record CHG-2058) | RSK-mu0t2oau (RSK-003) — Unauthorized developer exploits excessive privileges causing unapproved model changes to AI Model Training Server (linked on theme); secondary risk with no risk ID in source, referenced by title: “Incomplete validation exploits insufficient testing coverage causing defective models to advance from Pre-Production AI Validation Environment” | OBS-01 — Rollback-Plan Documentation (Process-Improvement Observation) | For change CHG-2058, the rollback-plan section of the change record was present but lacked sufficient detail. (Simulated.) | Observation | Process-Improvement Observation | Not separately rated; Risk / Impact: Low | Low | AI Engineering Team | AI Engineering Team | Adopt a standardized rollback-plan template within the change record so that rollback steps are consistently documented in sufficient detail. | Open (Simulated) — process improvement | Open (Simulated) | Not performed — evidence not provided | October 31, 2026 (Simulated) | 2026-10-31 | Exact date | Control-level evidence list EVD-012 to EVD-018 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Process-improvement observation — not a control exception; does not affect the attribute results or the Effective rating. | Simulated portfolio scenario
FRT-006 | OBS-01 | MAL-STD-004 | Privileged Access & Multi-Factor Authentication Security Standard | §9 | CTL-004 — Enforce multi-factor authentication and least-privilege access for privileged AI platform accounts (CIS 6) | Effective | AST-001, AST-002, AST-003, AST-004, AST-006, AST-007, AST-008, AST-009, AST-010 (in-scope assets per MAL-STD-004 §3) | RSK-mu0t2oau (RSK-003) — primary risk mitigated by this control (source-provided) | OBS-01 — Break-Glass Review Cadence (Minor) | The standard requires controlled emergency / break-glass access (§7.5), but a specific periodic review cadence for break-glass account usage has not yet been formally defined. | Observation | Process-Improvement Observation | Not separately rated; Risk / Impact: Low | Low | IAM Team | IAM Team | Establish a documented quarterly review of break-glass account activity, with review ownership, evidence retention, and escalation requirements. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | Q4 2026 |  | Quarter (text) | Control-level evidence list EVD-019 to EVD-027 (Evidence Requests tab); the source does not map items to this record | Verify the review requirement and supporting evidence during the next quarterly conformance assessment. | Not a control exception or a finding; does not change the Effective rating recorded in the Control Register. | Simulated portfolio scenario
FRT-007 | VUL-01 | MAL-VMA-005 | Vulnerability Management Control Assessment / Test Report | §10–11 | CTL-005 — Perform vulnerability testing and remediate identified weaknesses in production AI APIs (NIST CSF DE.CM-09) | Partially Effective | AST-001 — Clinical Diagnostic AI Model | RSK-004 and RSK-006 (nearest related risks; imperfect mapping — see Section 5 coverage gap) | VUL-01 — Scan Coverage Gap (Finding) | Authenticated monthly scanning is established for the in-scope production AI service, but the API/endpoint inventory is not consistently reconciled to the scan scope, so one or more production endpoints associated with AST-001 may be omitted from a given monthly cycle. (Simulated.) | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Application Security Team (execution), with Clinical AI & Machine Learning Team (asset-owner support) | Application Security Team | Reconcile the API/endpoint inventory to the authenticated scan scope each monthly cycle and add a coverage-completeness check that flags any production endpoint not covered by a scan in the period. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | November 30, 2026 (Simulated) | 2026-11-30 | Exact date | Control-level evidence list EVD-028 to EVD-034 (Evidence Requests tab); the source does not map items to this record | Re-confirm scope-to-inventory reconciliation and coverage evidence at the next monthly assessment. | Rating rests primarily on VUL-01 and VUL-02 (Partially Effective) | Simulated portfolio scenario
FRT-008 | VUL-02 | MAL-VMA-005 | Vulnerability Management Control Assessment / Test Report | §10–11 | CTL-005 — Perform vulnerability testing and remediate identified weaknesses in production AI APIs (NIST CSF DE.CM-09) | Partially Effective | AST-001 — Clinical Diagnostic AI Model | RSK-004 and RSK-006 (nearest related risks; imperfect mapping — see Section 5 coverage gap) | VUL-02 — Remediation Timeliness (Finding) | Identified vulnerabilities are tracked and risk-rated, but remediation SLA adherence is inconsistent: a subset of findings — including at least one higher-severity finding — exceeded their defined remediation windows before closure. (Simulated.) | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Application Security Team (tracking), with Clinical AI & Machine Learning Team (accountable for remediation) and AI Engineering Team (fixes) | Application Security Team | Enforce severity-based remediation SLAs, escalate overdue items to the asset owner and management, and report SLA-adherence metrics on the control’s monthly cadence. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | November 30, 2026 (Simulated) | 2026-11-30 | Exact date | Control-level evidence list EVD-028 to EVD-034 (Evidence Requests tab); the source does not map items to this record | Review SLA-adherence metrics and overdue-item aging at the next monthly assessment. | Rating rests primarily on VUL-01 and VUL-02 (Partially Effective) | Simulated portfolio scenario
FRT-009 | VUL-03 | MAL-VMA-005 | Vulnerability Management Control Assessment / Test Report | §10–11 | CTL-005 — Perform vulnerability testing and remediate identified weaknesses in production AI APIs (NIST CSF DE.CM-09) | Partially Effective | AST-001 — Clinical Diagnostic AI Model | RSK-004 and RSK-006 (nearest related risks; imperfect mapping — see Section 5 coverage gap) | VUL-03 — AI-Specific Security Testing Gap (Observation) | Conventional web/API vulnerability testing is performed, but the testing program does not yet include AI-specific abuse cases (for example, input/prompt validation and model-inference abuse) for the production AI API. (Simulated.) | Observation | Process-Improvement Observation | Low (Observation) | Low | Application Security Team | Application Security Team | Extend the testing program to include AI/LLM-specific test cases for production AI APIs, aligned to emerging AI-security testing guidance; pilot on the in-scope service first. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | Q4 2026 (Simulated) |  | Quarter (text) | Control-level evidence list EVD-028 to EVD-034 (Evidence Requests tab); the source does not map items to this record | Confirm AI-specific test cases and results at a subsequent assessment. | Contributes context; the Partially Effective rating rests primarily on VUL-01 and VUL-02. | Simulated portfolio scenario
FRT-010 | None assigned in source | MAL-VMA-005 | Vulnerability Management Control Assessment / Test Report | §5 | CTL-005 — Perform vulnerability testing and remediate identified weaknesses in production AI APIs (NIST CSF DE.CM-09) | Partially Effective | AST-001 — Clinical Diagnostic AI Model (control's in-scope asset) | None in register (coverage gap); nearest related: RSK-004 and RSK-006 | Risk-Register Coverage Gap — Exploitable Vulnerabilities in Production AI APIs | No risk record in the register specifically addresses exploitable vulnerabilities in production AI APIs — the exact exposure this control mitigates. This is a risk-register coverage gap: the control operates against a risk that is not explicitly represented in the register. | Observation | Risk-Register Coverage Gap | Not rated in source | Not Rated | Application Security Team (proposed owner of the recommended risk record) | Application Security Team | Add a risk record for “exploitable vulnerabilities in production AI APIs” (owner Application Security Team) and link CTL-005 to it. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Control-level evidence list EVD-028 to EVD-034 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Described in source as an observation carried to the consolidated tracker; no rating impact stated. | Simulated portfolio scenario
FRT-011 | PRV-01 | MAL-PIA-006 | AI Privacy Impact Assessment (DPIA-Aligned) | §11–12 | CTL-006 — Review AI datasets for unnecessary personal information and apply privacy safeguards before processing (GDPR Art.5) | Partially Effective | AST-002 (Stream A — financial training data); AST-001 and AST-009 (Stream B — clinical processing) | RSK-002 (Stream A) and RSK-008 (Stream B) — nearest related risks; imperfect, “loosely related” mapping (see Section 5 coverage gap) | PRV-01 — Data Minimization Gap (Finding) | The assessment scenario indicates that the quarterly minimization review does not consistently document whether all retained personal-data elements are necessary for the stated processing purpose; unnecessary personal data may therefore be retained without a documented justification. Applies across Stream A (AST-002) and the clinical Stream B (AST-001 / AST-009). | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Privacy and Compliance Team (review), with Data Science Team and Clinical AI & Machine Learning Team (asset owners) | Privacy and Compliance Team | For each in-scope dataset, maintain a data inventory mapping every personal-data element to a documented necessity justification tied to the processing purpose; remove or justify elements that are not necessary; record decisions each review cycle. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | December 31, 2026 (Simulated) | 2026-12-31 | Exact date | Control-level evidence list EVD-035 to EVD-041 (Evidence Requests tab); the source does not map items to this record | Re-confirm the documented necessity mapping and minimization decisions at the next quarterly review. | Rating rests primarily on PRV-01 and PRV-02 (Partially Effective) | Simulated portfolio scenario
FRT-012 | PRV-02 | MAL-PIA-006 | AI Privacy Impact Assessment (DPIA-Aligned) | §11–12 | CTL-006 — Review AI datasets for unnecessary personal information and apply privacy safeguards before processing (GDPR Art.5) | Partially Effective | AST-002 (Stream A — financial training data); AST-001 and AST-009 (Stream B — clinical processing) | RSK-002 (Stream A) and RSK-008 (Stream B) — nearest related risks; imperfect, “loosely related” mapping (see Section 5 coverage gap) | PRV-02 — Inconsistent Privacy Safeguards (Finding) | The assessment scenario indicates that privacy safeguards (for example, masking or pseudonymization of personal-data elements) are not consistently applied across all in-scope personal data before processing, and that the application of safeguards is not uniformly documented. | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Privacy and Compliance Team (standard), with Data Science Team / AI Engineering Team (implementation) and Data Protection Team (clinical backup) | Privacy and Compliance Team | Define a consistent safeguard standard (masking / pseudonymization and access restriction) for personal-data elements before processing, apply it across all in-scope datasets, and record the safeguards applied per dataset. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | December 31, 2026 (Simulated) | 2026-12-31 | Exact date | Control-level evidence list EVD-035 to EVD-041 (Evidence Requests tab); the source does not map items to this record | Review safeguard-application records per dataset at the next quarterly review. | Rating rests primarily on PRV-01 and PRV-02 (Partially Effective) | Simulated portfolio scenario
FRT-013 | PRV-03 | MAL-PIA-006 | AI Privacy Impact Assessment (DPIA-Aligned) | §11–12 | CTL-006 — Review AI datasets for unnecessary personal information and apply privacy safeguards before processing (GDPR Art.5) | Partially Effective | AST-002 (Stream A — financial training data); AST-001 and AST-009 (Stream B — clinical processing) | RSK-002 (Stream A) and RSK-008 (Stream B) — nearest related risks; imperfect, “loosely related” mapping (see Section 5 coverage gap) | PRV-03 — Retention / Storage Limitation (Observation) | The assessment scenario indicates that retention periods for personal data in the in-scope datasets are not yet formally defined or enforced, so data could be retained longer than necessary. | Observation | Process-Improvement Observation | Low (Observation) | Low | Privacy and Compliance Team | Privacy and Compliance Team | Define retention periods for personal data in each in-scope dataset aligned to the processing purpose, implement periodic deletion / review, and formalize a retention schedule. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | Q1 2027 (Simulated) |  | Quarter (text) | Control-level evidence list EVD-035 to EVD-041 (Evidence Requests tab); the source does not map items to this record | Confirm the retention schedule and enforcement evidence at a subsequent review. | Contributes context; the Partially Effective rating rests primarily on PRV-01 and PRV-02. | Simulated portfolio scenario
FRT-014 | None assigned in source | MAL-PIA-006 | AI Privacy Impact Assessment (DPIA-Aligned) | §5 | CTL-006 — Review AI datasets for unnecessary personal information and apply privacy safeguards before processing (GDPR Art.5) | Partially Effective | AST-002; AST-001; AST-009 (in-scope streams) | None in register (coverage gap); nearest related: RSK-002 and RSK-008 | Risk-Register Coverage Gap — Unnecessary Personal Data / Non-Compliant Processing in AI Datasets | No risk record in the register specifically addresses excessive or unnecessary personal data in AI datasets, or non-compliant processing of personal data — the exact exposure this control mitigates. This is a risk-register coverage gap: the control operates against a risk that is not explicitly represented in the register. | Observation | Risk-Register Coverage Gap | Not rated in source | Not Rated | Privacy and Compliance Team (proposed owner of the recommended risk record) | Privacy and Compliance Team | Add a risk record for “unnecessary personal data / non-compliant processing in AI datasets” (owner Privacy and Compliance Team) and link CTL-006 to it. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Control-level evidence list EVD-035 to EVD-041 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Described in source as an observation carried to the consolidated tracker; no rating impact stated. | Simulated portfolio scenario
FRT-015 | OBS-01 | MAL-BRT-007 | Backup & Recovery Test Record | §10 | CTL-007 — Maintain tested backup and recovery procedures for critical production AI systems (ISO 27001 A.5.30) | Effective | AST-001 (protected system); AST-009 (backup source); AST-010 (recovery environment) | RSK-007 — Infrastructure outage exploits inadequate recovery testing causing prolonged service disruption to AI Disaster Recovery Cloud Environment (primary risk; direct fit — no coverage gap claimed) | OBS-01 — RTO/RPO Metrics Documentation (Low / Process-Improvement Observation) | Within the simulated test scenario, recovery testing is represented as successfully completed; however, the test-record design does not include a standardized field for documenting formally approved RTO / RPO targets alongside measured recovery outcomes. | Observation | Process-Improvement Observation | Low | Low | Infrastructure Operations Team | Infrastructure Operations Team | Add standardized RTO / RPO target and actual-result fields to future quarterly recovery test records to strengthen repeatability, trend analysis, and management reporting. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | Q1 2027 (Simulated) |  | Quarter (text) | Control-level evidence list EVD-042 to EVD-049 (Evidence Requests tab); the source does not map items to this record | Confirm the enhanced RTO / RPO fields are present in the next quarterly recovery test record. | None; this is a process-improvement observation and does not affect the Effective rating. | Simulated portfolio scenario
FRT-016 | LOG-01 | MAL-LMA-008 | Security Logging & Monitoring Control Assessment | §10–11 | CTL-008 — Centralize and review security logs for suspicious activity affecting production AI systems (CIS 8) | Partially Effective | AST-001, AST-002, AST-007 (log sources); central logging capability has no distinct asset | RSK-006 — nearest register risk, with mapping limitation (network-access risk); RSK-002 and RSK-003 noted as detection scenarios only | LOG-01 — Log Source Coverage Gap (Finding) | The assessment scenario indicates that not all in-scope production AI systems consistently forward their security logs to the central logging capability; at least one in-scope source appears incompletely onboarded, so some security events may not reach central logging for review. | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Security Operations Team (central logging), with the relevant log-source / asset owners | Security Operations Team | Reconcile the in-scope production AI systems to the central logging source inventory; onboard any missing source; add a periodic coverage-completeness check that flags any in-scope system not forwarding logs. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | December 31, 2026 (Simulated) | 2026-12-31 | Exact date | Control-level evidence list EVD-050 to EVD-057 (Evidence Requests tab); the source does not map items to this record | Re-confirm source-to-inventory reconciliation and coverage evidence at the next review. | Conclusion driven primarily by LOG-01 and LOG-02 (Partially Effective) | Simulated portfolio scenario
FRT-017 | LOG-02 | MAL-LMA-008 | Security Logging & Monitoring Control Assessment | §10–11 | CTL-008 — Centralize and review security logs for suspicious activity affecting production AI systems (CIS 8) | Partially Effective | AST-001, AST-002, AST-007 (log sources); central logging capability has no distinct asset | RSK-006 — nearest register risk, with mapping limitation (network-access risk); RSK-002 and RSK-003 noted as detection scenarios only | LOG-02 — Log Review / Alert-Triage Timeliness (Finding) | The assessment scenario indicates that although logs are centralized, continuous review and alert triage are not consistently performed within a defined timeframe, and alerting thresholds for AI-relevant suspicious activity are not fully established. | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Security Operations Team | Security Operations Team | Define review / triage timeframes and alerting thresholds for suspicious activity on in-scope systems; document who reviews, how often, and escalation paths; report review / triage timeliness metrics. | In Progress (Simulated) | In Progress (Simulated) | Not performed — evidence not provided | December 31, 2026 (Simulated) | 2026-12-31 | Exact date | Control-level evidence list EVD-050 to EVD-057 (Evidence Requests tab); the source does not map items to this record | Review triage-timeliness metrics and alerting configuration at the next review. | Conclusion driven primarily by LOG-01 and LOG-02 (Partially Effective) | Simulated portfolio scenario
FRT-018 | LOG-03 | MAL-LMA-008 | Security Logging & Monitoring Control Assessment | §10–11 | CTL-008 — Centralize and review security logs for suspicious activity affecting production AI systems (CIS 8) | Partially Effective | AST-001, AST-002, AST-007 (log sources); central logging capability has no distinct asset | RSK-006 — nearest register risk, with mapping limitation (network-access risk); RSK-002 and RSK-003 noted as detection scenarios only | LOG-03 — AI-Specific Detection Use-Case Maturity (Observation) | The assessment scenario indicates that general security monitoring is established, but AI-specific detection use cases, such as anomalous model API access, unusual model-administration activity, or unexpected access patterns affecting AI data repositories, are not yet formally defined across the monitoring program. | Observation | Process-Improvement Observation | Low (Observation) | Low | Security Operations Team | Security Operations Team | Define and document prioritized AI-specific detection use cases for critical and high-classification production AI systems and incorporate them into the monitoring program’s detection and review procedures. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | Q1 2027 (Simulated) |  | Quarter (text) | Control-level evidence list EVD-050 to EVD-057 (Evidence Requests tab); the source does not map items to this record | Confirm defined AI-specific detection use-cases and their incorporation at a subsequent review. | None independently. The Partially Effective conclusion is driven primarily by LOG-01 and LOG-02. | Simulated portfolio scenario
FRT-019 | None assigned in source | MAL-LMA-008 | Security Logging & Monitoring Control Assessment | §5 | CTL-008 — Centralize and review security logs for suspicious activity affecting production AI systems (CIS 8) | Partially Effective | AST-001, AST-002, AST-007 (log sources in scope) | None in register (coverage gap); nearest related: RSK-006 | Risk-Register Coverage Gap — Undetected Suspicious Activity on Production AI Systems | No current Risk Register entry specifically represents the risk that suspicious or malicious activity affecting production AI systems remains undetected because security logs are incomplete, not centralized, or inadequately reviewed. | Observation | Risk-Register Coverage Gap | Not rated in source | Not Rated | Security Operations Team (proposed owner of the recommended risk record) | Security Operations Team | Add such a risk (owner Security Operations Team) and link CTL-008 to it. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Control-level evidence list EVD-050 to EVD-057 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Described in source as an observation carried to the consolidated tracker; no rating impact stated. | Simulated portfolio scenario
FRT-020 | None assigned in source | MAL-LMA-008 | Security Logging & Monitoring Control Assessment | §3 | CTL-008 — Centralize and review security logs for suspicious activity affecting production AI systems (CIS 8) | Partially Effective | None — no distinct central logging / SIEM platform in the Asset Register | None stated | Asset-Register Traceability Observation — No Central Logging Platform Identified | CTL-008 requires centralized security logging, but the current Asset Register does not identify a distinct central logging or SIEM platform. This assessment therefore evaluates the centralized logging capability as a control function operated by the Security Operations Team without assigning an unsupported platform or asset identifier. | Observation | Asset-Register Observation | Not rated in source | Not Rated | Not specified in source | Not specified in source | Consider adding the central logging platform to the Asset Register if it is maintained as a separately managed information asset. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Control-level evidence list EVD-050 to EVD-057 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Described in source as an observation carried to the consolidated tracker; no rating impact stated. | Simulated portfolio scenario
FRT-021 | APO-01 | MAL-CAP-009 | Compliance Assessment Plan & Evidence Request | §11 | CTL-009 — Perform documented compliance assessments of high-impact AI systems against applicable requirements (ISO 27001 A.5.31) | Not Tested | AST-001 (primary), AST-002 (supporting), AST-006 (reference only) — per MAL-CAP-009 §3 | No dedicated risk in register; nearest (imperfect) risk referenced by title only: “Incomplete validation exploits insufficient testing coverage causing defective models to advance from Pre-Production AI Validation Environment” | APO-01 — Incomplete Control Documentation | The source control record does not expose a description or rationale, and the register does not define “high-impact AI system.” | Planning Gap | Planning Observation | Not rated in source | Not Rated | Not specified in source | Not specified in source | Confirm the authoritative control description, high-impact definition, and expected evidence before testing. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Not specified in source — PBC list (EVD-058 to EVD-069) is control-level; the source does not map PBC items to planning observations | Not Defined in Source | None — planning observation, not a finding or control deficiency; no effectiveness conclusion drawn (Not Concluded). | Simulated portfolio scenario
FRT-022 | APO-02 | MAL-CAP-009 | Compliance Assessment Plan & Evidence Request | §11 | CTL-009 — Perform documented compliance assessments of high-impact AI systems against applicable requirements (ISO 27001 A.5.31) | Not Tested | AST-001 (primary), AST-002 (supporting), AST-006 (reference only) — per MAL-CAP-009 §3 | No dedicated risk in register; nearest (imperfect) risk referenced by title only: “Incomplete validation exploits insufficient testing coverage causing defective models to advance from Pre-Production AI Validation Environment” | APO-02 — Responsible AI Policy Not Finalized | POL-006 (Responsible AI and Human Oversight Policy) has a source status of Under Review. | Planning Gap | Planning Observation | Not rated in source | Not Rated | Not specified in source | Not specified in source | Confirm the approved version and status before using it as formal assessment criteria. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Not specified in source — PBC list (EVD-058 to EVD-069) is control-level; the source does not map PBC items to planning observations | Not Defined in Source | None — planning observation, not a finding or control deficiency; no effectiveness conclusion drawn (Not Concluded). | Simulated portfolio scenario
FRT-023 | APO-03 | MAL-CAP-009 | Compliance Assessment Plan & Evidence Request | §11 (see also §6.2) | CTL-009 — Perform documented compliance assessments of high-impact AI systems against applicable requirements (ISO 27001 A.5.31) | Not Tested | AST-001 (primary), AST-002 (supporting), AST-006 (reference only) — per MAL-CAP-009 §3 | No dedicated risk in register; nearest (imperfect) risk referenced by title only: “Incomplete validation exploits insufficient testing coverage causing defective models to advance from Pre-Production AI Validation Environment” | APO-03 — Compliance Risk Coverage Gap | No dedicated risk addresses failure to assess high-impact AI systems against applicable requirements. | Planning Gap | Planning Observation | Not rated in source | Not Rated | GRC Team (proposed owner of the recommended risk record) | GRC Team | Consider a dedicated compliance risk owned by the GRC Team, linked to CTL-009. Carry to the Findings & Remediation Tracker. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Not specified in source — PBC list (EVD-058 to EVD-069) is control-level; the source does not map PBC items to planning observations | Not Defined in Source | None — planning observation, not a finding or control deficiency; no effectiveness conclusion drawn (Not Concluded). | Simulated portfolio scenario
FRT-024 | APO-04 | MAL-CAP-009 | Compliance Assessment Plan & Evidence Request | §11 (see also §6.3) | CTL-009 — Perform documented compliance assessments of high-impact AI systems against applicable requirements (ISO 27001 A.5.31) | Not Tested | AST-001 (primary), AST-002 (supporting), AST-006 (reference only) — per MAL-CAP-009 §3 | No dedicated risk in register; nearest (imperfect) risk referenced by title only: “Incomplete validation exploits insufficient testing coverage causing defective models to advance from Pre-Production AI Validation Environment” | APO-04 — Compliance Risk Appetite Coverage | No dedicated Compliance appetite statement is represented in the available risk-appetite records. | Planning Gap | Planning Observation | Not rated in source | Not Rated | Not specified in source | Not specified in source | Confirm whether compliance risk is governed under another approved appetite category or whether a dedicated statement should be established. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Not specified in source — PBC list (EVD-058 to EVD-069) is control-level; the source does not map PBC items to planning observations | Not Defined in Source | None — planning observation, not a finding or control deficiency; no effectiveness conclusion drawn (Not Concluded). | Simulated portfolio scenario
FRT-025 | VRA-01 | MAL-VRA-010 | Third-Party AI Vendor Risk Assessment | §11–12 | CTL-010 — Assess security and privacy risks before approving third-party AI vendors and services (SOC 2 CC9.2) | Ineffective | None established in source (no register asset is a vendor; AST-001 would be relevant only if a third-party AI service accessed it — no such relationship is asserted) | No primary risk in register (coverage gap, §5.1); no vendor-to-risk linkage established in source | VRA-01 — Pre-Approval Assessment Not Consistently Performed and Documented (Finding) | The simulated scenario indicates that third-party AI vendors and services subject to approval during the assessment period can proceed to approval without a completed and documented security and privacy risk assessment, or with the assessment completed after the approval decision. (Simulated.) | Confirmed Finding (Simulated) | Control Deficiency (Finding) | High | High | Third-Party Risk Management Team, with Privacy and Compliance Team support | Third-Party Risk Management Team | Establish a mandatory pre-approval gate under which no vendor or service is approved or onboarded without a completed, documented security and privacy assessment and recorded sign-off. Assess retrospectively any approved vendors and services that lack an assessment, starting with those handling sensitive data. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | November 30, 2026 (Simulated) | 2026-11-30 | Exact date | Source-stated via attribute mapping: EVD-074 (EV-05), EVD-075 (EV-06), EVD-076 (EV-07), EVD-077 (EV-08), EVD-078 (EV-09), EVD-079 (EV-10), EVD-080 (EV-11), EVD-081 (EV-12) | Re-perform against the approval population for the next assessment period and confirm every approval is preceded by a completed assessment. | Primary driver of the Ineffective conclusion. | Simulated portfolio scenario
FRT-026 | VRA-02 | MAL-VRA-010 | Third-Party AI Vendor Risk Assessment | §11–12 | CTL-010 — Assess security and privacy risks before approving third-party AI vendors and services (SOC 2 CC9.2) | Ineffective | None established in source (no register asset is a vendor; AST-001 would be relevant only if a third-party AI service accessed it — no such relationship is asserted) | No primary risk in register (coverage gap, §5.1); no vendor-to-risk linkage established in source | VRA-02 — Vendor Risk Assessment Criteria and Tiering Not Defined (Finding) | The simulated scenario indicates that no defined vendor risk-tiering methodology or consistent security and privacy assessment criteria for AI vendors and services are in place, so assessment depth is not set by vendor criticality or data sensitivity. (Simulated.) | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Third-Party Risk Management Team, with Privacy and Compliance Team and Information Security Team consulted | Third-Party Risk Management Team | Define a vendor tiering methodology and minimum security and privacy assessment criteria for AI services (for example, data handling, model and data-use terms, incident notification, and sub-processor use), with assessment depth tied to tier. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | December 31, 2026 (Simulated) | 2026-12-31 | Exact date | Source-stated via attribute mapping: EVD-072 (EV-03), EVD-073 (EV-04) | Confirm the approved methodology and criteria are applied to new approval requests at the next assessment. | Contributing deficiency. | Simulated portfolio scenario
FRT-027 | VRA-03 | MAL-VRA-010 | Third-Party AI Vendor Risk Assessment | §11–12 | CTL-010 — Assess security and privacy risks before approving third-party AI vendors and services (SOC 2 CC9.2) | Ineffective | None established in source (no register asset is a vendor; AST-001 would be relevant only if a third-party AI service accessed it — no such relationship is asserted) | No primary risk in register (coverage gap, §5.1); no vendor-to-risk linkage established in source | VRA-03 — Third-Party Governance Documentation and Inventory Gap (Finding) | The simulated scenario indicates that third-party AI governance is not supported by a documented third-party risk policy within the available Policy Register, and the available source records do not provide a vendor/service inventory from which the population subject to CTL-010 can be established. | Confirmed Finding (Simulated) | Control Deficiency (Finding) | Medium | Medium | Third-Party Risk Management Team, with GRC Team support for policy governance | Third-Party Risk Management Team | Establish documented third-party AI risk governance requirements and maintain an authoritative inventory of third-party AI vendors and services subject to security and privacy assessment. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | December 31, 2026 (Simulated) | 2026-12-31 | Exact date | Source-stated via attribute mapping: EVD-070 (EV-01), EVD-071 (EV-02), EVD-074 (EV-05) | Confirm an approved policy and an inventory reconciled to the approval population. | Contributing design / governance deficiency. | Simulated portfolio scenario
FRT-028 | VRA-04 | MAL-VRA-010 | Third-Party AI Vendor Risk Assessment | §11–12 | CTL-010 — Assess security and privacy risks before approving third-party AI vendors and services (SOC 2 CC9.2) | Ineffective | None established in source (no register asset is a vendor; AST-001 would be relevant only if a third-party AI service accessed it — no such relationship is asserted) | No primary risk in register (coverage gap, §5.1); no vendor-to-risk linkage established in source | VRA-04 — Ongoing Third-Party Monitoring Maturity (Observation) | The simulated scenario indicates that monitoring and reassessment of vendors and services after approval are not clearly defined beyond KRI-006 reporting. (Simulated.) | Observation | Process-Improvement Observation | Low (Observation) | Low | Third-Party Risk Management Team | Third-Party Risk Management Team | Define reassessment triggers and frequency by vendor tier and link them to KRI-006 reporting. | Open (Simulated) | Open (Simulated) | Not performed — evidence not provided | Q1 2027 (Simulated) |  | Quarter (text) | Source-stated via attribute mapping: EVD-082 (EV-13) | Confirm defined reassessment triggers at a subsequent assessment. | None independently. | Simulated portfolio scenario
FRT-029 | None assigned in source | MAL-VRA-010 | Third-Party AI Vendor Risk Assessment | §5.3 | CTL-010 — Assess security and privacy risks before approving third-party AI vendors and services (SOC 2 CC9.2) | Ineffective | None established in source | None in register (coverage gap) | Risk-Register Coverage Gap — Third-Party AI Vendor and Service Risk | The Risk Register does not contain a risk specifically addressing failure to identify, assess, approve, or monitor security and privacy risks associated with third-party AI vendors and services. | Observation | Risk-Register Coverage Gap | Not rated in source | Not Rated | Third-Party Risk Management Team (proposed owner of the recommended risk record) | Third-Party Risk Management Team | Establish a dedicated third-party risk owned by the Third-Party Risk Management Team and link CTL-010 as a mitigating control. No identifier is assigned to this proposed risk because it is not in the register. | Not stated in source | No Status in Source | Not performed — evidence not provided | Not stated in source |  | Not stated in source | Control-level evidence list EVD-070 to EVD-083 (Evidence Requests tab); the source does not map items to this record | Not Defined in Source | Described in source as a coverage gap carried to the consolidated tracker; no rating impact stated. | Simulated portfolio scenario

## Remediation Actions
Remediation Actions
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
One row per source recommendation. No actions, dates or completions have been added beyond what the source documents state.
Action ID | Linked Tracker ID | Original Source ID | Source Document ID | Linked Classification | Linked Severity (As Documented) | Action Description (As Documented) | Action Owner (As Documented) | Action Status (As Documented) | Reported Status Group (Analyst-Derived) | Target Date (As Documented) | Target Date (Exact) | Validation Step (Source) | Completion Evidence Received | Independent Closure Validation | Simulation Flag
REM-001 | FRT-001 | OBS-01 | MAL-CHK-001 | Observation | Not separately rated; Risk / Impact: Low | Continue monitoring field completeness in future quarterly validations and confirm the field remains excluded from model input. | Data Science Team | Records retained; reviewed and accepted by the Data Science Team | Accepted by Owner (per source) | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-002 | FRT-002 | ACR-01 | MAL-ACR-002 | Confirmed Finding (Simulated) | Medium | Revoke the retained entitlements and incorporate mover events into the joiner/mover/leaver (JML) process, with HR-triggered, automated recalculation of access on role change. | IAM Team (execution), with Data Science Team (resource-owner approval) | In Progress (Simulated) | In Progress (Simulated) | October 31, 2026 (Simulated) | 2026-10-31 | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-003 | FRT-003 | ACR-02 | MAL-ACR-002 | Confirmed Finding (Simulated) | Medium-High | Downgrade both accounts to read-only; enforce the authoritative role-to-entitlement mapping; require documented business justification and periodic recertification for any write-level access. | IAM Team (execution), with Data Science Team (resource-owner approval) | In Progress (Simulated) | In Progress (Simulated) | October 31, 2026 (Simulated) | 2026-10-31 | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-004 | FRT-004 | ACR-03 | MAL-ACR-002 | Confirmed Finding (Simulated) | High (window) | Account disablement for contractor test identity C-207 — as reported in the source status field (“account disabled”). Not a separate recommendation in the source. | IAM Team (execution), with HR / Vendor Management (notification of end dates) | Remediated (Simulated) — account disabled | Reported Remediated (Simulated) | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-005 | FRT-004 | ACR-03 | MAL-ACR-002 | Confirmed Finding (Simulated) | High (window) | Implement event-driven deprovisioning tied to contract end dates; perform leaver reconciliation each quarter; generate alerts for any account active past its associated end date. | IAM Team (execution), with HR / Vendor Management (notification of end dates) | Open — underlying process fix (per source status: “underlying process fix Open”) | Open (Simulated) | November 15, 2026 (Simulated) for the process fix | 2026-11-15 | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-006 | FRT-005 | OBS-01 | MAL-CTW-003 | Observation | Not separately rated; Risk / Impact: Low | Adopt a standardized rollback-plan template within the change record so that rollback steps are consistently documented in sufficient detail. | AI Engineering Team | Open (Simulated) — process improvement | Open (Simulated) | October 31, 2026 (Simulated) | 2026-10-31 | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-007 | FRT-006 | OBS-01 | MAL-STD-004 | Observation | Not separately rated; Risk / Impact: Low | Establish a documented quarterly review of break-glass account activity, with review ownership, evidence retention, and escalation requirements. | IAM Team | Open (Simulated) | Open (Simulated) | Q4 2026 |  | Verify the review requirement and supporting evidence during the next quarterly conformance assessment. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-008 | FRT-007 | VUL-01 | MAL-VMA-005 | Confirmed Finding (Simulated) | Medium | Reconcile the API/endpoint inventory to the authenticated scan scope each monthly cycle and add a coverage-completeness check that flags any production endpoint not covered by a scan in the period. | Application Security Team (execution), with Clinical AI & Machine Learning Team (asset-owner support) | In Progress (Simulated) | In Progress (Simulated) | November 30, 2026 (Simulated) | 2026-11-30 | Re-confirm scope-to-inventory reconciliation and coverage evidence at the next monthly assessment. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-009 | FRT-008 | VUL-02 | MAL-VMA-005 | Confirmed Finding (Simulated) | Medium | Enforce severity-based remediation SLAs, escalate overdue items to the asset owner and management, and report SLA-adherence metrics on the control’s monthly cadence. | Application Security Team (tracking), with Clinical AI & Machine Learning Team (accountable for remediation) and AI Engineering Team (fixes) | In Progress (Simulated) | In Progress (Simulated) | November 30, 2026 (Simulated) | 2026-11-30 | Review SLA-adherence metrics and overdue-item aging at the next monthly assessment. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-010 | FRT-009 | VUL-03 | MAL-VMA-005 | Observation | Low (Observation) | Extend the testing program to include AI/LLM-specific test cases for production AI APIs, aligned to emerging AI-security testing guidance; pilot on the in-scope service first. | Application Security Team | Open (Simulated) | Open (Simulated) | Q4 2026 (Simulated) |  | Confirm AI-specific test cases and results at a subsequent assessment. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-011 | FRT-010 | None assigned in source | MAL-VMA-005 | Observation | Not rated in source | Add a risk record for “exploitable vulnerabilities in production AI APIs” (owner Application Security Team) and link CTL-005 to it. | Application Security Team (proposed owner of the recommended risk record) | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-012 | FRT-011 | PRV-01 | MAL-PIA-006 | Confirmed Finding (Simulated) | Medium | For each in-scope dataset, maintain a data inventory mapping every personal-data element to a documented necessity justification tied to the processing purpose; remove or justify elements that are not necessary; record decisions each review cycle. | Privacy and Compliance Team (review), with Data Science Team and Clinical AI & Machine Learning Team (asset owners) | In Progress (Simulated) | In Progress (Simulated) | December 31, 2026 (Simulated) | 2026-12-31 | Re-confirm the documented necessity mapping and minimization decisions at the next quarterly review. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-013 | FRT-012 | PRV-02 | MAL-PIA-006 | Confirmed Finding (Simulated) | Medium | Define a consistent safeguard standard (masking / pseudonymization and access restriction) for personal-data elements before processing, apply it across all in-scope datasets, and record the safeguards applied per dataset. | Privacy and Compliance Team (standard), with Data Science Team / AI Engineering Team (implementation) and Data Protection Team (clinical backup) | In Progress (Simulated) | In Progress (Simulated) | December 31, 2026 (Simulated) | 2026-12-31 | Review safeguard-application records per dataset at the next quarterly review. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-014 | FRT-013 | PRV-03 | MAL-PIA-006 | Observation | Low (Observation) | Define retention periods for personal data in each in-scope dataset aligned to the processing purpose, implement periodic deletion / review, and formalize a retention schedule. | Privacy and Compliance Team | Open (Simulated) | Open (Simulated) | Q1 2027 (Simulated) |  | Confirm the retention schedule and enforcement evidence at a subsequent review. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-015 | FRT-014 | None assigned in source | MAL-PIA-006 | Observation | Not rated in source | Add a risk record for “unnecessary personal data / non-compliant processing in AI datasets” (owner Privacy and Compliance Team) and link CTL-006 to it. | Privacy and Compliance Team (proposed owner of the recommended risk record) | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-016 | FRT-015 | OBS-01 | MAL-BRT-007 | Observation | Low | Add standardized RTO / RPO target and actual-result fields to future quarterly recovery test records to strengthen repeatability, trend analysis, and management reporting. | Infrastructure Operations Team | Open (Simulated) | Open (Simulated) | Q1 2027 (Simulated) |  | Confirm the enhanced RTO / RPO fields are present in the next quarterly recovery test record. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-017 | FRT-016 | LOG-01 | MAL-LMA-008 | Confirmed Finding (Simulated) | Medium | Reconcile the in-scope production AI systems to the central logging source inventory; onboard any missing source; add a periodic coverage-completeness check that flags any in-scope system not forwarding logs. | Security Operations Team (central logging), with the relevant log-source / asset owners | In Progress (Simulated) | In Progress (Simulated) | December 31, 2026 (Simulated) | 2026-12-31 | Re-confirm source-to-inventory reconciliation and coverage evidence at the next review. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-018 | FRT-017 | LOG-02 | MAL-LMA-008 | Confirmed Finding (Simulated) | Medium | Define review / triage timeframes and alerting thresholds for suspicious activity on in-scope systems; document who reviews, how often, and escalation paths; report review / triage timeliness metrics. | Security Operations Team | In Progress (Simulated) | In Progress (Simulated) | December 31, 2026 (Simulated) | 2026-12-31 | Review triage-timeliness metrics and alerting configuration at the next review. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-019 | FRT-018 | LOG-03 | MAL-LMA-008 | Observation | Low (Observation) | Define and document prioritized AI-specific detection use cases for critical and high-classification production AI systems and incorporate them into the monitoring program’s detection and review procedures. | Security Operations Team | Open (Simulated) | Open (Simulated) | Q1 2027 (Simulated) |  | Confirm defined AI-specific detection use-cases and their incorporation at a subsequent review. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-020 | FRT-019 | None assigned in source | MAL-LMA-008 | Observation | Not rated in source | Add such a risk (owner Security Operations Team) and link CTL-008 to it. | Security Operations Team (proposed owner of the recommended risk record) | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-021 | FRT-020 | None assigned in source | MAL-LMA-008 | Observation | Not rated in source | Consider adding the central logging platform to the Asset Register if it is maintained as a separately managed information asset. | Not specified in source | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-022 | FRT-021 | APO-01 | MAL-CAP-009 | Planning Gap | Not rated in source | Confirm the authoritative control description, high-impact definition, and expected evidence before testing. | Not specified in source | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-023 | FRT-022 | APO-02 | MAL-CAP-009 | Planning Gap | Not rated in source | Confirm the approved version and status before using it as formal assessment criteria. | Not specified in source | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-024 | FRT-023 | APO-03 | MAL-CAP-009 | Planning Gap | Not rated in source | Consider a dedicated compliance risk owned by the GRC Team, linked to CTL-009. Carry to the Findings & Remediation Tracker. | GRC Team (proposed owner of the recommended risk record) | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-025 | FRT-024 | APO-04 | MAL-CAP-009 | Planning Gap | Not rated in source | Confirm whether compliance risk is governed under another approved appetite category or whether a dedicated statement should be established. | Not specified in source | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-026 | FRT-025 | VRA-01 | MAL-VRA-010 | Confirmed Finding (Simulated) | High | Establish a mandatory pre-approval gate under which no vendor or service is approved or onboarded without a completed, documented security and privacy assessment and recorded sign-off. Assess retrospectively any approved vendors and services that lack an assessment, starting with those handling sensitive data. | Third-Party Risk Management Team, with Privacy and Compliance Team support | Open (Simulated) | Open (Simulated) | November 30, 2026 (Simulated) | 2026-11-30 | Re-perform against the approval population for the next assessment period and confirm every approval is preceded by a completed assessment. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-027 | FRT-026 | VRA-02 | MAL-VRA-010 | Confirmed Finding (Simulated) | Medium | Define a vendor tiering methodology and minimum security and privacy assessment criteria for AI services (for example, data handling, model and data-use terms, incident notification, and sub-processor use), with assessment depth tied to tier. | Third-Party Risk Management Team, with Privacy and Compliance Team and Information Security Team consulted | Open (Simulated) | Open (Simulated) | December 31, 2026 (Simulated) | 2026-12-31 | Confirm the approved methodology and criteria are applied to new approval requests at the next assessment. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-028 | FRT-027 | VRA-03 | MAL-VRA-010 | Confirmed Finding (Simulated) | Medium | Establish documented third-party AI risk governance requirements and maintain an authoritative inventory of third-party AI vendors and services subject to security and privacy assessment. | Third-Party Risk Management Team, with GRC Team support for policy governance | Open (Simulated) | Open (Simulated) | December 31, 2026 (Simulated) | 2026-12-31 | Confirm an approved policy and an inventory reconciled to the approval population. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-029 | FRT-028 | VRA-04 | MAL-VRA-010 | Observation | Low (Observation) | Define reassessment triggers and frequency by vendor tier and link them to KRI-006 reporting. | Third-Party Risk Management Team | Open (Simulated) | Open (Simulated) | Q1 2027 (Simulated) |  | Confirm defined reassessment triggers at a subsequent assessment. | None provided | Not performed — evidence not provided | Simulated portfolio scenario
REM-030 | FRT-029 | None assigned in source | MAL-VRA-010 | Observation | Not rated in source | Establish a dedicated third-party risk owned by the Third-Party Risk Management Team and link CTL-010 as a mitigating control. No identifier is assigned to this proposed risk because it is not in the register. | Third-Party Risk Management Team (proposed owner of the recommended risk record) | Not stated in source | No Status in Source | Not stated in source |  | Not Defined in Source | None provided | Not performed — evidence not provided | Simulated portfolio scenario

## Evidence Requests
Evidence Requests
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
Evidence requirements are kept separate from findings. A missing evidence item is not, by itself, a control deficiency.
Evidence Tracker ID | Original Evidence ID | Source Document ID | Source Section | Related Control | Evidence Item (As Documented) | Source Status (As Documented) | Requested From (As Documented) | Linked Attribute (Source) | Linked Record(s) — Source-Stated | Link Basis | Evidence Received | Treated as Control Deficiency? | Simulation Flag
EVD-001 | None assigned in source | MAL-CHK-001 | §8 | CTL-mu0tgvxq (ISO 27001 A.5.12) | Data quality profiling report | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-002 | None assigned in source | MAL-CHK-001 | §8 | CTL-mu0tgvxq (ISO 27001 A.5.12) | Bias / representativeness assessment summary | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-003 | None assigned in source | MAL-CHK-001 | §8 | CTL-mu0tgvxq (ISO 27001 A.5.12) | Data lineage documentation | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-004 | None assigned in source | MAL-CHK-001 | §8 | CTL-mu0tgvxq (ISO 27001 A.5.12) | Data classification report | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-005 | None assigned in source | MAL-CHK-001 | §8 | CTL-mu0tgvxq (ISO 27001 A.5.12) | Access-review confirmation (authorized-personnel listing) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-006 | None assigned in source | MAL-ACR-002 | §12 | CTL-mu1nugzu (NIST CSF PR.AA-05) | Current IAM entitlement listing (system export) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-007 | None assigned in source | MAL-ACR-002 | §12 | CTL-mu1nugzu (NIST CSF PR.AA-05) | Authoritative role-to-entitlement mapping | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-008 | None assigned in source | MAL-ACR-002 | §12 | CTL-mu1nugzu (NIST CSF PR.AA-05) | HR and vendor joiner/mover/leaver change report (Q3 2026) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-009 | None assigned in source | MAL-ACR-002 | §12 | CTL-mu1nugzu (NIST CSF PR.AA-05) | Access-request approval records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-010 | None assigned in source | MAL-ACR-002 | §12 | CTL-mu1nugzu (NIST CSF PR.AA-05) | Deprovisioning tickets and timestamps | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-011 | None assigned in source | MAL-ACR-002 | §12 | CTL-mu1nugzu (NIST CSF PR.AA-05) | Privileged-access activity logs | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-012 | None assigned in source | MAL-CTW-003 | §12 | CTL-mu1nvfmw (SOC 2 CC8.1) | Change-management records / tickets for the sampled changes | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-013 | None assigned in source | MAL-CTW-003 | §12 | CTL-mu1nvfmw (SOC 2 CC8.1) | Pre-deployment test results | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-014 | None assigned in source | MAL-CTW-003 | §12 | CTL-mu1nvfmw (SOC 2 CC8.1) | Approval records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-015 | None assigned in source | MAL-CTW-003 | §12 | CTL-mu1nvfmw (SOC 2 CC8.1) | Deployment logs / timestamps | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-016 | None assigned in source | MAL-CTW-003 | §12 | CTL-mu1nvfmw (SOC 2 CC8.1) | Segregation-of-duties / role configuration | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-017 | None assigned in source | MAL-CTW-003 | §12 | CTL-mu1nvfmw (SOC 2 CC8.1) | Post-deployment verification records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-018 | None assigned in source | MAL-CTW-003 | §12 | CTL-mu1nvfmw (SOC 2 CC8.1) | Population listing of production model changes for the assessment period | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-019 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Identity provider / MFA enforcement policy export for privileged roles | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-020 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Privileged role and entitlement definitions per platform (cloud IAM, server, application, data-store, network device) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-021 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Privileged access request and approval records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-022 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | PAM / just-in-time access configuration and elevation-grant records (where applicable) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-023 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Break-glass / emergency-access procedure and usage records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-024 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Privileged access recertification records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-025 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Provisioning / deprovisioning (joiner-mover-leaver) records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-026 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Privileged authentication and administrative-action logs (central log management) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-027 | None assigned in source | MAL-STD-004 | §11 | CTL-004 (CIS Controls v8, Control 6) | Exception register entries for deviations from this standard | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-028 | None assigned in source | MAL-VMA-005 | §14 | CTL-005 (NIST CSF DE.CM-09) | Authenticated vulnerability-scan reports for in-scope production AI APIs (monthly) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-029 | None assigned in source | MAL-VMA-005 | §14 | CTL-005 (NIST CSF DE.CM-09) | API / endpoint inventory reconciled to scan scope | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-030 | None assigned in source | MAL-VMA-005 | §14 | CTL-005 (NIST CSF DE.CM-09) | Vulnerability findings register with severity ratings | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-031 | None assigned in source | MAL-VMA-005 | §14 | CTL-005 (NIST CSF DE.CM-09) | Remediation tickets with timestamps and SLA tracking | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-032 | None assigned in source | MAL-VMA-005 | §14 | CTL-005 (NIST CSF DE.CM-09) | Retest / closure evidence for remediated findings | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-033 | None assigned in source | MAL-VMA-005 | §14 | CTL-005 (NIST CSF DE.CM-09) | AI-specific security test cases and results (where applicable) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-034 | None assigned in source | MAL-VMA-005 | §14 | CTL-005 (NIST CSF DE.CM-09) | Vulnerability-management procedure and remediation-SLA policy | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-035 | None assigned in source | MAL-PIA-006 | §15 | CTL-006 (GDPR Art.5) | Data inventory / field-level data dictionary for each in-scope dataset | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-036 | None assigned in source | MAL-PIA-006 | §15 | CTL-006 (GDPR Art.5) | Records of processing activities (ROPA) for the in-scope processing | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-037 | None assigned in source | MAL-PIA-006 | §15 | CTL-006 (GDPR Art.5) | Quarterly data-minimization review records and necessity justifications | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-038 | None assigned in source | MAL-PIA-006 | §15 | CTL-006 (GDPR Art.5) | Masking / pseudonymization configuration and safeguard-application records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-039 | None assigned in source | MAL-PIA-006 | §15 | CTL-006 (GDPR Art.5) | Retention schedule and deletion / enforcement evidence | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-040 | None assigned in source | MAL-PIA-006 | §15 | CTL-006 (GDPR Art.5) | Lawful-basis / purpose documentation and data-subject transparency notices | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-041 | None assigned in source | MAL-PIA-006 | §15 | CTL-006 (GDPR Art.5) | Special-category (clinical) data safeguards and any applicable authorization / consent records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-042 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Backup job completion records / schedule | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-043 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Backup integrity / validation reports (e.g., checksums) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-044 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Restore logs from the recovery test | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-045 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Service-recovery / failover records for the recovery environment | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-046 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Post-restore data-validation results | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-047 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Measured recovery-time (RTO) and recovery-point (RPO) results against defined targets | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-048 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Backup & recovery procedure and DR runbook | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-049 | None assigned in source | MAL-BRT-007 | §12 | CTL-007 (ISO 27001 A.5.30) | Backup retention / rotation policy and evidence | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-050 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | Central logging / SIEM configuration and log-source inventory | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-051 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | Log-forwarding / collection configuration for in-scope systems | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-052 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | Sample centralized log records demonstrating coverage | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-053 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | Detection / alerting rule configuration and thresholds | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-054 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | Alert review / triage records and timeliness metrics | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-055 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | Log retention configuration and evidence | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-056 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | Documented audit-log management and monitoring procedures | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-057 | None assigned in source | MAL-LMA-008 | §14 | CTL-008 (CIS Controls v8, Control 8) | AI-specific detection use-case definitions (where applicable) | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Not stated in source | Control-level only | Source does not map this item to a specific finding | No | No — evidence requirement only | Simulated portfolio scenario
EVD-058 | PBC-01 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | High-impact AI system inventory and classification methodology | Evidence Required — Not Provided (Simulated Requirement) | GRC Team / AI Governance Team | Planned attribute A1 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-059 | PBC-02 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Current applicable-requirements register | Evidence Required — Not Provided (Simulated Requirement) | GRC Team | Planned attribute A2 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-060 | PBC-03 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Prior annual compliance assessment(s), if any | Evidence Required — Not Provided (Simulated Requirement) | GRC Team | Planned attribute A3, A8 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-061 | PBC-04 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Approved POL-001, POL-002, and the applicable final Responsible AI policy | Evidence Required — Not Provided (Simulated Requirement) | AI Governance Team / Data Governance Team | Planned attribute A4 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-062 | PBC-05 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | System-specific compliance and control mappings | Evidence Required — Not Provided (Simulated Requirement) | GRC Team / Clinical AI & ML Team | Planned attribute A4 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-063 | PBC-06 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Assessment checklists and workpapers | Evidence Required — Not Provided (Simulated Requirement) | GRC Team | Planned attribute A3, A4 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-064 | PBC-07 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Identified compliance gaps and remediation records | Evidence Required — Not Provided (Simulated Requirement) | GRC Team / system owners | Planned attribute A5 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-065 | PBC-08 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Governance or committee reporting showing assessment results | Evidence Required — Not Provided (Simulated Requirement) | GRC Team | Planned attribute A6 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-066 | PBC-09 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Evidence of management review and sign-off | Evidence Required — Not Provided (Simulated Requirement) | GRC Team management | Planned attribute A6 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-067 | PBC-10 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Material-change records showing whether reassessment was triggered | Evidence Required — Not Provided (Simulated Requirement) | Clinical AI & ML Team / Machine Learning Engineering | Planned attribute A7 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-068 | PBC-11 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Evidence supporting applicable legal and regulatory determinations | Evidence Required — Not Provided (Simulated Requirement) | GRC Team / Privacy and Compliance Team | Planned attribute A2 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-069 | PBC-12 | MAL-CAP-009 | §12 | CTL-009 (ISO 27001 A.5.31) | Prior-period follow-up or closure evidence | Evidence Required — Not Provided (Simulated Requirement) | GRC Team | Planned attribute A8 | None (CAP-009 has no findings; planning observations are not mapped to PBC items) | Source-stated attribute link (MAL-CAP-009 §9, §12) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-070 | EV-01 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Authoritative vendor / service inventory | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 2 | VRA-03 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-071 | EV-02 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Third-party risk management policy / procedure | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 3 | VRA-03 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-072 | EV-03 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Vendor risk-tiering methodology | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 4 | VRA-02 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-073 | EV-04 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Security and privacy assessment criteria | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 5 | VRA-02 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-074 | EV-05 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Population of third-party AI vendor / service approval requests for the assessment period | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 2, 6 | VRA-03, VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-075 | EV-06 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Completed pre-approval assessments | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 6, 7 | VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-076 | EV-07 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Security questionnaires | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 6 | VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-077 | EV-08 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Privacy / data-processing assessments | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 6 | VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-078 | EV-09 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Independent assurance reports, where applicable | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 6 | VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-079 | EV-10 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Contracts and security / privacy terms | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 6, 8 | VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-080 | EV-11 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Approval records demonstrating the assessment occurred before approval | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 7 | VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-081 | EV-12 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Identified vendor risks and remediation or acceptance records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 8 | VRA-01 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-082 | EV-13 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | Ongoing monitoring and reassessment records | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 9 | VRA-04 | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario
EVD-083 | EV-14 | MAL-VRA-010 | §15 | CTL-010 (SOC 2 CC9.2) | KRI-006 source data and calculation methodology | Evidence Required — Not Provided (Simulated Requirement) | Not specified in source | Control attribute 10 | None (attribute 10 is Met (Source); no finding) | Source-stated: evidence-to-attribute (§15) and attribute-to-finding (§9) | No | No — evidence requirement only | Simulated portfolio scenario

## Source Index
Source Index & Reconciliation
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
“Documented” counts were counted from each source document; “Extracted” counts are live formulas over the Findings and Evidence Requests tabs.
Document ID | Document Title | Version | Document Date (Revision History) | Control Reference | Framework Reference | Control Owner | Control Rating / Conclusion (Source) | Document Status (Source) | Documented Findings | Documented Observations (incl. coverage-gap observations) | Documented Planning Gaps | Documented Evidence Items | Extracted Findings | Extracted Observations | Extracted Planning Gaps | Extracted Evidence Items | Reconciliation | Source File (Uploaded)
MAL-CHK-001 | AI Training Data Validation Checklist | 1.0 | 2026-09-14 | CTL-mu0tgvxq | ISO 27001 A.5.12 | Data Science Team | Effective | Completed (Simulated) — Sign-Off Pending | 0 | 1 | 0 | 5 | 0 | 1 | 0 | 5 | Match | MAL-CHK-001_AI_Training_Data_Validation_Checklist.docx
MAL-ACR-002 | User Access Review Worksheet | 1.0 | 2026-09-15 | CTL-mu1nugzu | NIST CSF PR.AA-05 | IAM Team | Partially Effective | Completed (Simulated) — Sign-Off Pending | 3 | 0 | 0 | 6 | 3 | 0 | 0 | 6 | Match | MAL-ACR-002_User_Access_Review_Worksheet.docx
MAL-CTW-003 | Change Management Control Test Worksheet | 1.0 | 2026-09-15 | CTL-mu1nvfmw | SOC 2 CC8.1 | AI Engineering Team | Effective | Completed (Simulated) — Sign-Off Pending | 0 | 1 | 0 | 7 | 0 | 1 | 0 | 7 | Match | MAL-CTW-003_Change_Management_Control_Test_Worksheet.docx
MAL-STD-004 | Privileged Access & Multi-Factor Authentication Security Standard | 1.0 | 2026-09-17 | CTL-004 | CIS Controls v8, Control 6 | IAM Team | Effective | Final — Portfolio Simulation | 0 | 1 | 0 | 9 | 0 | 1 | 0 | 9 | Match | MAL-STD-004_Privileged_Access_and_MFA_Security_Standard.docx
MAL-VMA-005 | Vulnerability Management Control Assessment / Test Report | 1.0 | 2026-09-26 | CTL-005 | NIST CSF DE.CM-09 | Application Security Team | Partially Effective | Final — Portfolio Simulation | 2 | 2 | 0 | 7 | 2 | 2 | 0 | 7 | Match | MAL-VMA-005_Vulnerability_Management_Control_Assessment.docx
MAL-PIA-006 | AI Privacy Impact Assessment (DPIA-Aligned) | 1.0 | 2026-09-26 | CTL-006 | GDPR Art.5 | Privacy and Compliance Team | Partially Effective | Final — Portfolio Simulation | 2 | 2 | 0 | 7 | 2 | 2 | 0 | 7 | Match | MAL-PIA-006_AI_Privacy_Impact_Assessment.docx
MAL-BRT-007 | Backup & Recovery Test Record | 1.0 | 2026-09-26 | CTL-007 | ISO 27001 A.5.30 | Infrastructure Operations Team | Effective | Final — Portfolio Simulation | 0 | 1 | 0 | 8 | 0 | 1 | 0 | 8 | Match | MAL-BRT-007_Backup_and_Recovery_Test_Record.docx
MAL-LMA-008 | Security Logging & Monitoring Control Assessment | 1.0 | 2026-09-26 | CTL-008 | CIS Controls v8, Control 8 | Security Operations Team | Partially Effective | Final — Portfolio Simulation | 2 | 3 | 0 | 8 | 2 | 3 | 0 | 8 | Match | MAL-LMA-008_Security_Logging_and_Monitoring_Control_Assessment.docx
MAL-CAP-009 | Compliance Assessment Plan & Evidence Request | 1.0 | 2026-09-27 | CTL-009 | ISO 27001 A.5.31 | GRC Team | Not Tested (Effectiveness Not Concluded) | Final — Portfolio Simulation | 0 | 0 | 4 | 12 | 0 | 0 | 4 | 12 | Match | MAL-CAP-009_Compliance_Assessment_Plan_and_Evidence_Request.docx
MAL-VRA-010 | Third-Party AI Vendor Risk Assessment | 1.0 | 2026-09-27 | CTL-010 | SOC 2 CC9.2 | Third-Party Risk Management Team | Ineffective | Final — Portfolio Simulation | 3 | 2 | 0 | 14 | 3 | 2 | 0 | 14 | Match | MAL-VRA-010_Third-Party_AI_Vendor_Risk_Assessment.docx
TOTAL | [8 empty] | 12 | 13 | 4 | 83 | 12 | 13 | 4 | 83 | All Match
Note: MAL-IPR-011 is not listed because its assessment document was not provided. Document dates are the version 1.0 dates in each document’s Revision History. Documents 001–003 carry the status “Completed (Simulated) — Sign-Off Pending”; sign-off tables in all ten documents are blank or not applicable.

## ID Crosswalk
ID Crosswalk
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
Source (export) IDs ↔ normalized IDs. A normalized ID appears only where a source document states it; otherwise “Not stated in source documents”. Risks without IDs are referenced by title.
A. Assets (Asset Register; normalized IDs stated in MAL-STD-004 §3)
Normalized ID | Source ID (JSON export) | Asset Name | Type | Classification | Environment | Records Referencing (live count) | Owner
AST-001 | AST-mu0s8cur | Clinical Diagnostic AI Model | Application | Critical | Production | 23 | Clinical AI & Machine Learning Team
AST-002 | AST-mu0set5n | Financial Risk Training Data Repository | Data Store | High | Production | 17 | Data Science Team
AST-003 | AST-mu0sfsup | AI Model Training Server | Server | Medium | Development | 1 | Machine Learning Engineering
AST-004 | Not exposed in source (null) | AI Development Cloud Environment | Cloud Account | Medium | Development | 1 | Cloud Engineering
AST-005 | Not exposed in source (null) | AI Governance Analyst Workstation | Endpoint | Low | Production | 0 | AI Governance Team
AST-006 | Not exposed in source (null) | Pre-Production AI Validation Environment | Server | Medium | Staging | 5 | Model Validation Team
AST-007 | Not exposed in source (null) | AI Network Security Gateway | Network Device | High | Production | 5 | Network Security Team
AST-008 | Not exposed in source (null) | Pre-Production Model Validation Server | Server | Medium | Staging | 1 | Model Validation Team
AST-009 | Not exposed in source (null) | Clinical AI Backup Repository | Data Store | High | DR | 6 | Data Protection Team
AST-010 | Not exposed in source (null) | AI Disaster Recovery Cloud Environment | Cloud Account | High | DR | 2 | Cloud Operations Team
AST-011 | Not exposed in source (null) | Model Testing Workstation | Endpoint | Low | Staging | 0 | AI Quality Assurance Team
B. Risks (Risk Register; likelihood / impact as exported — no scores or tolerance comparisons computed)
Normalized ID | Source ID (JSON export) | Risk Title | Category | Status (Register) | Likelihood | Impact | Owner | Where Cited in Source Documents
RSK-001 | RSK-mu0sxjrj | Training data bias causes inaccurate clinical AI recommendations | Data Protection | Open | 3 | 5 | Clinical AI & Machine Learning Team | MAL-PIA-006 §5
RSK-002 | RSK-mu0t1uva | Unauthorized user exploits inadequate data access restrictions causing sensitive data exposure to Financial Risk Training Data Repository | Data Protection | Open | 3 | 4 | Data Science Team | MAL-PIA-006 §5; MAL-LMA-008 §5
RSK-003 | RSK-mu0t2oau | Unauthorized developer exploits excessive privileges causing unapproved model changes to AI Model Training Server | Access Control | In Progress | 3 | 4 | Machine Learning Engineering | MAL-LMA-008 §5
RSK-004 | Not exposed in source (null) | Cloud misconfiguration exploits weak configuration governance causing unauthorized resource exposure to AI Development Cloud Environment | Application Security | Open | 4 | 3 | Cloud Engineering | MAL-VMA-005 §5
Not stated in source documents | Not exposed in source (null) | Incomplete validation exploits insufficient testing coverage causing defective models to advance from Pre-Production AI Validation Environment | Compliance | In Progress | 3 | 4 | Model Validation Team | Referenced by title only (MAL-CTW-003 §4; MAL-CAP-009 §6.1)
RSK-006 | Not exposed in source (null) | External attacker exploits weak network filtering causing unauthorized AI infrastructure access through AI Network Security Gateway | Access Control | In Progress | 2 | 5 | Network Security Team | MAL-VMA-005 §5; MAL-LMA-008 §5
RSK-007 | Not exposed in source (null) | Infrastructure outage exploits inadequate recovery testing causing prolonged service disruption to AI Disaster Recovery Cloud Environment | Availability | Open | 2 | 5 | Cloud Operations Team | MAL-BRT-007 §5
RSK-008 | Not exposed in source (null) | Unauthorized user exploits inadequate backup access controls causing sensitive data exposure to Clinical AI Backup Repository | Data Protection | Open | 2 | 4 | Data Protection Team | MAL-PIA-006 §5; MAL-BRT-007 §5
Not stated in source documents | Not exposed in source (null) | Phishing attacker exploits user error causing unauthorized governance data access to AI Governance Analyst Workstation | Human Error | Closed | 3 | 2 | AI Governance Team | Not cited by any in-scope source document
Not stated in source documents | Not exposed in source (null) | Tester exploits excessive system privileges causing unauthorized validation changes to Pre-Production Model Validation Server | Access Control | Closed | 2 | 3 | Model Validation Team | Referenced by description only (MAL-STD-004 §4)
Not stated in source documents | Not exposed in source (null) | Analyst error exploits inadequate test review procedures causing inaccurate validation results to Model Testing Workstation | Human Error | Closed | 3 | 2 | AI Quality Assurance Team | Not cited by any in-scope source document
C. Controls (Control Register)
Normalized ID | Source ID (JSON export) | Control Name | Framework Ref | Rating (Register) | Frequency |  | Owner | Tracker Source Document
Not stated in source documents | CTL-mu0tgvxq | Perform documented bias and data quality validation before AI model approval | ISO 27001 A.5.12 | Effective | Quarterly |  | Data Science Team | MAL-CHK-001
Not stated in source documents | CTL-mu1nugzu | Restrict AI training data repositories to authorized personnel using role-based access | NIST CSF PR.AA-05 | Partially Effective | Quarterly |  | IAM Team | MAL-ACR-002
Not stated in source documents | CTL-mu1nvfmw | Require documented review and approval before production AI model changes are deployed | SOC 2 CC8.1 | Effective | Continuous |  | AI Engineering Team | MAL-CTW-003
CTL-004 | Not exposed in source (null) | Enforce multi-factor authentication and least-privilege access for privileged AI platform accounts | CIS Controls CIS 6 | Effective | Continuous |  | IAM Team | MAL-STD-004
CTL-005 | Not exposed in source (null) | Perform vulnerability testing and remediate identified weaknesses in production AI APIs | NIST CSF DE.CM-09 | Partially Effective | Monthly |  | Application Security Team | MAL-VMA-005
CTL-006 | Not exposed in source (null) | Review AI datasets for unnecessary personal information and apply privacy safeguards before processing | GDPR Art.5 | Partially Effective | Quarterly |  | Privacy and Compliance Team | MAL-PIA-006
CTL-007 | Not exposed in source (null) | Maintain tested backup and recovery procedures for critical production AI systems | ISO 27001 A.5.30 | Effective | Quarterly |  | Infrastructure Operations Team | MAL-BRT-007
CTL-008 | Not exposed in source (null) | Centralize and review security logs for suspicious activity affecting production AI systems | CIS Controls CIS 8 | Partially Effective | Continuous |  | Security Operations Team | MAL-LMA-008
CTL-009 | Not exposed in source (null) | Perform documented compliance assessments of high-impact AI systems against applicable requirements | ISO 27001 A.5.31 | Not Tested | Annual |  | GRC Team | MAL-CAP-009
CTL-010 | Not exposed in source (null) | Assess security and privacy risks before approving third-party AI vendors and services | SOC 2 CC9.2 | Ineffective | Continuous |  | Third-Party Risk Management Team | MAL-VRA-010
Not stated in source documents | Not exposed in source (null) | Require independent peer review of AI model testing results before production approval | ISO 27001 A.5.35 | Not Tested | Quarterly |  | AI Quality Assurance Team | Not included — MAL-IPR-011 assessment document not provided
D. Policies cited by source documents (Policies export)
Policy ID | Title |  | Status (Export) | Owner |  |  | Cited In
POL-001 | AI Model Risk Management and Validation Policy |  | Approved | AI Governance Team |  |  | MAL-CAP-009 §5 (candidate criteria)
POL-002 | AI Data Governance and Quality Policy |  | Approved | Data Governance Team |  |  | MAL-CAP-009 §5 (candidate criteria)
POL-006 | Responsible AI and Human Oversight Policy |  | Under Review | AI Governance Team |  |  | MAL-CAP-009 §5, APO-02
MAL-VRA-010 (VRA-03) states that no third-party risk policy exists within the available Policy Register; none of POL-001 to POL-006 in the export addresses third-party risk.

## Data Dictionary
Data Dictionary
SIMULATED GRC PRACTICE ENVIRONMENT — All findings, observations, planning gaps, statuses, target dates and assessment results in this workbook belong to a simulated portfolio scenario (MindfulAI Labs). They do not represent verified production-system testing, actual evidence, management approvals, or an actual organization.
Column definitions for Findings, Remediation Actions, Evidence Requests and Source Index. “Source-verbatim” = copied from the source document; “Analyst-derived” = reporting classification only.
Tab | Column | Definition | Allowed Values / Format | Origin
Findings | Tracker ID | Unique ID assigned by this tracker to avoid conflicts (e.g., four documents each contain an “OBS-01”). | FRT-001 to FRT-029 | Tracker-assigned
Findings | Original Source ID | The ID printed in the source document. | e.g., ACR-01, VUL-02, OBS-01, APO-03; “None assigned in source” where the document gives no ID | Source-verbatim
Findings | Source Document ID / Title / Section | The artifact and section from which the record was extracted, for traceability. | MAL-xxx-0nn; § reference | Source-verbatim
Findings | Related Control | Control ID, name and framework reference as stated in the source document and Control Register. | CTL-mu… (documents 001–003) or CTL-004 to CTL-010 | Source-verbatim
Findings | Control Rating (Source Register) | Effectiveness rating recorded for the control in the Control Register as cited by the document. | Effective, Partially Effective, Ineffective, Not Tested | Source-verbatim
Findings | Related Asset / Related Risk | Assets and risks the source document links to the record. Risks without IDs are cited by title. | Free text | Source-verbatim
Findings | Title (As Documented) | Finding or observation heading as printed in the source (prefixed with the original ID where one exists). | Free text | Source-verbatim
Findings | Description (As Documented) | Condition / observation text copied from the source. | Free text | Source-verbatim
Findings | Classification | Nature of the record. | Confirmed Finding (Simulated) ¦ Observation ¦ Planning Gap | Analyst-derived
Findings | Subtype | Finer label following the source wording. | Control Deficiency (Finding) ¦ Control Deficiency (Exception) ¦ Process-Improvement Observation ¦ Minor Observation (source label) ¦ Risk-Register Coverage Gap ¦ Asset-Register Observation ¦ Planning Observation | Analyst-derived
Findings | Severity (As Documented) | Severity or risk wording exactly as in the source, including “Medium-High” and “High (window)”. Where the source gives only a Risk / Impact of Low, that is stated. | Free text | Source-verbatim
Findings | Severity Group (Analyst-Derived) | Grouping used for filtering and dashboard counts. Not a source rating. | High ¦ Medium-High ¦ Medium ¦ Low ¦ Not Rated | Analyst-derived
Findings | Owner (As Documented) | Owner / execution responsibility exactly as written in the source. For coverage gaps, the owner proposed in the source for the recommended risk record. | Free text; “Not specified in source” | Source-verbatim
Findings | Primary Owner Team (Analyst-Derived) | First-named team, used for dashboard owner counts. | Team name; “Not specified in source” | Analyst-derived
Findings | Recommended Action (As Documented) | Recommendation or planning action copied from the source. | Free text | Source-verbatim
Findings | Status (As Documented) | Status stated in the source. “Not stated in source” where none is given. | e.g., In Progress (Simulated); Open (Simulated); Remediated (Simulated) — account disabled; underlying process fix Open | Source-verbatim
Findings | Reported Status Group (Analyst-Derived) | Grouping of the documented status for counting. Never implies independent validation. | In Progress (Simulated) ¦ Open (Simulated) ¦ Reported Remediated (Sim.) — Process Fix Open ¦ Accepted by Owner (per source) ¦ No Status in Source | Analyst-derived
Findings | Independent Closure Validation | Whether closure was independently validated. No evidence exists in this simulated scenario. | Not performed — evidence not provided | Tracker-assigned
Findings | Target Date (As Documented) | Target text exactly as documented, including quarter-only targets. | Free text | Source-verbatim
Findings | Target Date (Exact) | Populated only when the source gives a calendar date. Quarter targets are never converted. | yyyy-mm-dd or blank | Source-verbatim
Findings | Target Date Type | Whether the target is an exact date, a quarter (text) or not stated. | Exact date ¦ Quarter (text) ¦ Not stated in source | Analyst-derived
Findings | Evidence Required (Cross-Reference) | Pointer to the related Evidence Requests rows. Item-level links are shown only where the source states them (MAL-VRA-010); otherwise the link is control-level. | Evidence Tracker IDs | Analyst-derived
Findings | Closure Criteria | The source “Validation” statement verbatim; otherwise “Not Defined in Source”. No criteria have been generated. | Free text | Source-verbatim
Findings | Rating Impact (As Documented) | Effect on the control rating as stated by the source. | Free text | Source-verbatim
Findings | Simulation Flag | Marks every record as a simulated portfolio scenario. | Simulated portfolio scenario | Tracker-assigned
Remediation Actions | Action ID | Unique action ID. | REM-001 to REM-030 | Tracker-assigned
Remediation Actions | Linked Tracker ID | Finding / observation / planning-gap record the action belongs to. | FRT-nnn | Tracker-assigned
Remediation Actions | Linked Classification / Linked Severity | Looked up from the Findings tab. | Formula | Formula
Remediation Actions | Action Description (As Documented) | Source recommendation. ACR-03 is split into (a) the account disablement reported in the source status and (b) the recommended process fix, because the source reports different statuses for each. | Free text | Source-verbatim
Remediation Actions | Completion Evidence Received | No completion evidence exists in the source documents. | None provided | Tracker-assigned
Evidence Requests | Evidence Tracker ID / Original Evidence ID | Tracker ID, and the PBC-nn / EV-nn ID where the source uses one. | EVD-001 to EVD-083 | Tracker-assigned
Evidence Requests | Evidence Item / Source Status | Wording and status exactly as in the source evidence tables. | Evidence Required — Not Provided (Simulated Requirement) | Source-verbatim
Evidence Requests | Linked Attribute / Linked Record(s) / Link Basis | Links stated by the source: CAP-009 maps PBC items to planned attributes; VRA-010 maps evidence to attributes and attributes to findings. Other documents give control-level lists only. | Free text | Source-verbatim
Evidence Requests | Treated as Control Deficiency? | Always “No — evidence requirement only”: missing evidence is not converted into a deficiency. | No — evidence requirement only | Tracker-assigned
Source Index | Documented vs. Extracted counts | Documented = counted by reading the source; Extracted = live COUNTIFS over this workbook; Reconciliation compares them. | Match ¦ Review | Formula